Appendix 1

Project classification code: SOM/SOM/20/011/REG

Project title: Innovations for smart and sustainable cities in ASEAN and Russia

Project description: In the 21st century, issues related to overpopulation, social inequality, food security, rapid urbanization, and other challenges to sustainable development have become extremely urgent for the South-East Asia region. According to the UN report, these challenges hamper ASEAN welfare convergence relative to advanced Asia. While ASEAN is a diverse and rapidly changing region that is experiencing progress across many aspects of the 2030 Agenda for Sustainable Development, the scale of the challenges ahead to achieve the SDGs is significant. In order to address the most crucial issues of sustainable development, ASEAN launched Smart Cities Network and ASEAN SDGs Frontrunner Cities initiatives, as well as plans to digitize various sectors of the economy, such as ASEAN Digital Integration Framework, Master Plan on ASEAN Connectivity 2025 and others. For Russia, these challenges are also becoming increasingly relevant, the issue of climate change being particularly acute. According to the estimates of Federal Service for Hydrometeorology and Environmental Monitoring (Rosgidromet), global warming in the Russian Federation is approximately 2.5 times more intense than the global average. A particular challenge for the urban planning in Russia is sustainable reorganization of large cities amid continued pressure caused by urban growth. These and other issues of sustainable development are among the key topics on the Russian agenda, which is reflected in the Voluntary National Review of progress towards the Sustainable Development Goals, which was presented at The United Nations High-level Political Forum on Sustainable Development in July, 2020. These challenges led to Russia stepping up its efforts on implementation of such national projects as “Digital Economy of the Russian Federation”, “Ecology”, “Smart City”, etc. Therefore, the matter of developing bilateral regional cooperation between ASEAN and Russia to facilitate the financing of technologies and the implementation of projects in the field of smart cities and sustainable development becomes more urgent. There is a need for the mutual exchange of experience, best practices, technologies, as well as the development of joint investment projects. However, to ensure the efficiency of such cooperation, it is necessary to create convenient platforms for interaction and work out viable formats in consultation with a wide range of experts from the states of the region. Such platforms should have a high level of transparency, credibility and mutual trust and help reduce costs, which is achieved through the use of new digital technologies. Main objectives of the project: - Identify potential of using digital technologies to promote investment cooperation in the field of innovations for smart and sustainable cities; - Create innovative tools and approaches to improve efficiency and transparency of interaction between city officials, projects and impact investors from ASEAN and Russia in the field of impact investment and technology exchange; - Promote introduction of digital technologies in the urban economy of ASEAN Member States and Russia for the benefit of sustainable development; - Deepen partnership in the field of innovative development of smart and sustainable cities between ASEAN and Russia; - Develop a roadmap on measures and pathways to facilitate technological exchange and implementation of joint pilot projects in cities of ASEAN and Russia. The project consists of three basic components: applied research in collaboration with ASEAN experts, development of a digital finance module and an international conference with experts, startups and investors from ASEAN Member States and Russia, as well as representatives of international organizations and regional authorities. The project will be implemented within: А. Comprehensive Plan of Action to Promote Cooperation Between The Association of Southeast Asian Nations and The Russian Federation (2016-2020) – II. Economic cooperation (46., 50.,.51., 53.) B. Sochi Declaration of the ASEAN-Russian Federation Commemorative Summit to Mark the 20th Anniversary of ASEAN-Russian Federation Dialogue Partnership “Moving Towards a Strategic Partnership for Mutual Benefit” - Economic Cooperation (31.) С. Joint Statement of the 3​​rd​​ ASEAN-Russian Federation Summit on Strategic Partnership (20.) Commitment to bilateral cooperation in this field is also evidenced by participation of Russian representatives in the technology exhibition on the sidelines of the East Asia Summit top-level events in Singapore in November 2018, as well as the participation of ASEAN representatives in the international forum “Smart City, Application Guide” in Kaluga in March 2019. This project will make reference and support, where relevant, the following ASEAN strategic documents: 1. ASEAN AEC Blueprint 2025: C. Enhanced Connectivity and Sectoral Cooperation. 2. ASCC Blueprint 2025: C2. Environmentally Sustainable Cities, actions (51) Innovation: Support ICT innovations and entrepreneurship as well as new technological developments such as Smart City, and Big Data and Analytics; and 3. ASCN-related documents, such as the ASCN Concept Note and Smart City Action Plans. 4. ASEAN Digital Integration Framework 5. Master Plan on ASEAN Connectivity (MPAC) 2025 under Initiative 3 on Sustainable Urbanisation. The following factors determine the relevance of the project: - On 14 July 2020 Russia presented its Voluntary National Review of progress towards the Sustainable Development Goals. At the same time, according to the report of the UN Economic and Social Commission for Asia and the Pacific (ESCAP), the SEA region is lagging behind in implementing the SDGs. Thus, both for ASEAN and for the Russian Federation, development of a tool for supporting sustainable projects and the intensification of comprehensive cooperation in this area is extremely relevant. - Conducting applied research will help to identify the most relevant and effective formats for development of cooperation in the field of smart and sustainable cities between ASEAN Member States and Russia, which meets the interests of the parties to strengthen cooperation in this sphere. In addition, the results of the research will be sent to representatives of the ASEAN Smart Cities Network (ASCN), ASEAN Digital Integration Framework, Master Plan on ASEAN Connectivity 2025 and other regional initiatives with the aim of providing methodological support to the development of relevant approaches to digitalization of urban economy in the countries of the region. - Digitalization of urban economy associated with creation of digital solutions is a global trend, as evidenced by relevant studies by the International Telecommunication Union, OECD and the World Economic Forum. According to the UN Task Force on Digital Financing of Sustainable Development Goals, digitalization and development of digital technologies for impact investment offer tremendous potential to help achieve the SDGs, especially in developing countries. In this regard, development of a digital finance module with monitoring features in the field of smart sustainable city projects of ASEAN and Russia will be a timely measure. - One of the factors hindering the introduction of innovative and sustainable solutions in cities is the difficulty in attracting financing and mutual distrust between investors and sustainable projects. The proposed project will accelerate this process by providing a convenient and transparent platform for interaction of all the parties. In addition, the digital finance module may facilitate the influx of impact investments in the SEA region and in Russia to help achieve the SDGs. - Large technological projects may encounter serious problems during implementation due to unfair fulfillment of the obligations by a certain party. The digital finance module will provide a framework to connect the data on the project impact with the financial parameters (such as interest rate of a bond) which will increase trust and transparency of sustainable investment projects. Project Stages - Research. To identify the potential of using digital technologies for promoting investment cooperation in the field of smart and sustainable cities of ASEAN and Russia, an applied study will be conducted in collaboration with experts from ASEAN Member States. The main objective of the study is to analyze the best global and regional experience and develop the most effective format for enhancing cooperation in the field of smart and sustainable cities between ASEAN and Russia, as well as provide specific recommendations for creating a digital finance module. The results of the study will form the basis for further stages of the Project. In addition, a network of specialized international experts will be formed with the potential to develop and scale up their activities in a format of a joint analytical center in the field of smart and sustainable cities. This will help develop cooperation within the framework of the National Project “Digital Economy of the Russian Federation” and such regional projects as ASEAN Digital Integration Framework and the Master Plan on ASEAN Connectivity 2025. The research will include the following stages: Primary data collection - Interviews with companies from ASEAN and Russia to identify urgent challenges for the development of smart and sustainable cities, as well as to assess the potential for implementing digital technologies to support national sustainable development programs (Sample: 5 to 10 interviews with representatives of IT / sustainable development departments of companies from ASEAN and Russia. Industries: metallurgy, energy, food industry); - Interviews with representatives of banks and companies that have experience in issuing green bonds in the ASEAN region, to collect primary data on the issuance of green bonds, to analyze their experience and identify key problems they encountered (Sample: 2 to 5 banks and companies); - Interviews with experts in the field of green financing (representatives of development banks, impact funds, universities, international organizations, NGOs and expert centers) to identify key market problems and digitalization potential to solve these problems (Sample: from 5 to 10 Russian and international experts). Secondary data collection - Collection of economic data on investments in sustainable development and digital technologies, as well as on the structure of foreign trade of selected countries (ASEAN Member States, Russia); - Collection of secondary data on the volume of issuance of green bonds and other instruments to support sustainable projects in ASEAN Member States; - Collection of secondary data on impact investments in sustainable projects of selected countries; - Collection of secondary data on smart cities and smart city projects in selected countries (data on priority sectors, on the complementarity of technologies in ASEAN Member States and Russia, etc.) Data analysis - Qualitative and quantitative analysis of the collected data to identify the impact of the introduction of digital technologies on achieving sustainable development goals. The research will involve specialists from ASEAN Member States and Russia. The expected participants include ASEAN Center at MGIMO (Russia), Singapore University of Management (Singapore), Nanyang University of Technology (Singapore), Cagayan State University (Philippines), Bogor Institute of Agriculture (Indonesia), New Era University (Philippines), Vietnam National University (Vietnam), etc. 2. Digital Finance Module A digital finance module will be developed to increase the efficiency and transparency of interaction between city authorities, projects and impact investors from ASEAN and Russia in the field of impact investment , as well as to promote the introduction of digital finance technologies in the urban economies of ASEAN Member States and Russia for the benefit of sustainable development. The digital finance module will be developed using industry 4.0 technologies based on the recommendations of the study, as well as UNFCCC methodological principles. The main purpose of the digital finance module is to facilitate financing and monitor the implementation and impact of smart and sustainable ASCN projects implemented through the module. The module will complement the ASCN online platform and smart and sustainable city investment toolkit that ASEAN. Representatives of innovative companies and investment projects in the field of smart and sustainable cities from ASEAN Member States and Russia will be able to attract finance from international investors by issuing digital green or sustainability-linked bonds. The module also allows monitoring of their environmental, social and economic impact in accordance with the UN SDGs. To test and demonstrate the functionality of the digital finance module, a pilot project in the field of smart agriculture will be implemented in partnership with a local partner (with possible involvement of multinational companies that have farming production in the region like Unilever, Mars, etc.). The pilot project will demonstrate the functionality of concluding digital transactions, investing in the project and its further monitoring. The pilot project will implement the following example scenario: the farm owner considers farmland expansion and / or introduction of sustainable agriculture practices. An investor signs a digital agreement on investing in this agricultural project and provides money. Since the implementation of such a pilot project is consistent with the 2nd Sustainable Development Goal (Zero Hunger), and in 2015 ASEAN Member States adopted guidelines for the development of smart agriculture, such a pilot is fully consistent with the basic principles of this Project and contributes to sustainable development of ASEAN smart cities. In addition to this pilot, other cases may be implemented by the Contractor during the implementation of the Project and subsequently presented at the international Conference. The contractor will be operating and maintaining the digital finance module during and upon the completion of the project. The costs for maintaining the digital finance module will be covered by commission fees that the key stakeholders will pay annually to use the platform. The key stakeholders could include those interested in using the digital finance module such as: commercial and national banks, arranging green and sustainability-linked bond issuances and monitoring in the ASEAN Member States, development finance institutions, international corporations and impact funds investing in sustainability projects in the region. The module could also be available for the project developers in the region that want to attract funding and explore innovative solutions. The digital finance module can also be used by the ASCN to complement the ASCN online platform and smart and sustainable city investment toolkit by ASEAN. The contractor will be constantly and responsibly managing the digital finance module as a part of its strategic business activities, and in line with the priorities and needs of ASCN cities. The use of blockchain technology on the digital finance module will increase the cyber security of operations, preventing malicious users from accessing important data and documents, as well as increasing its resistance to hacker attacks. In addition, the module may consider the integration of monitoring technologies (drones, sensors, satellite images) with blockchain, which is of particular value for monitoring the implementation of joint projects as it can increase transparency of data storage. In addition, blockchain technology enables faster and more cost-efficient issuance and circulation of digital financial instruments, including green bonds, green certificates, carbon credits, etc. - International conference International Conference on Innovations for Smart and Sustainable Cities will be held in Kuala Lumpur, depending on the international and regional COVID-19 pandemic situation, the Conference could be converted to a virtual format. The Conference will be held with the participation of representatives of the ASCN, Russian/ASEAN municipal authorities, government officials of relevant departments, investment funds, companies developing innovative technological solutions as well as representatives of international organizations, including UN agencies. The Conference will be held within two days. During the first day, high level meetings and negotiations between representatives of relevant departments and city authorities will be held. They will be dedicated to joint approaches and common standards for the development, financing and regulation of projects in the field of digitalization of smart and sustainable cities. The second day will be devoted to cooperation within the private sector. Pitch sessions will be held for the innovators to present their solutions to investors, city representatives and private companies. The results of the study, as well as concrete proposals to ASEAN representatives on the development of further cooperation within the Project will also be presented and discussed at the Conference. In addition, several functions of the digital finance module will be presented, namely: structuring of a programmable digital bond, issuance of a digital sustainability-linked bond with a floating interest rate, as well as monitoring of the use of proceeds . The Conference will host a pitch session for innovative companies where they will be able to present their solutions for further piloting in the smart cities of ASEAN and Russia, as well as attracting investment and securing partnerships. . The pitch session program will take place along three main tracks: - Agriculture & forestry - Infrastructure - Energy Working languages: English, Russian Results. As a result of the project, applied research and a functioning digital finance module that will complement the future ASCN online portal and smart and sustainable city investment toolkit should be created. The further development of the digital finance module is expected to be carried out in close consultation with ASEAN representatives. Strengthening trade and economic cooperation between ASEAN and Russia is expected, as well as conclusion of new partnership agreements, which will be facilitated by the pitch session at the conference. High-level delegates will have an avenue for discussing cooperation policies in the field of smart cities.

Supervising Authority of ASEAN: ASEAN Senior Officials’ Meeting (SOM) Sector committee / main body: ASEAN Senior Officials’ Meeting (SOM) Number and date of the meeting: Ad-referendum endorsement on 11 June 2021 Working group / Subcommittee Number and date of the meeting: N/A

Project initiator Ministry of Economic Development of the Russian Federation Number and date of submission of the project proposal to the ICG or the ASEAN Secretariat:

Date of submission: 15 December 2020

Name and details of the project initiator: Ministry of Economic Development of the Russian Federation, Department of Multilateral Economic Cooperation and Special Projects. 125039, Moscow, Presnenskaya nab., 10, building 2 Tel .: +7 (495) 870-29-21, ext. 13000 E-mail: Stapran@economy.gov.ru Natalia Stapran, Director of the Department

Name and details of the project executor: Limited Liability Company «Evercity» 105082, Moscow, Bakuninskaya street, 69, building 1 Tel.: +7(909) 927-21-59 E-mail: Dbelov@evercity.io Dmitry Belov, Project Manager

Estimated project cost and funding source (s): 281,135.80 USD Source: ASEAN-Russian Federation Dialogue Partnership Financial Fund

Recommendation by the Secretary General / ASEAN Project Appraisal Committee Number and date of the meeting: Ad-ref / 6 January 2021 PAC ad-referendum endorsement on 8 January 2021

Expertise and recommendation of the specialized body from Russia / Interdepartmental Coordination Group: Number and date of the meeting: Ministry of Finance of the Russian Federation (№ 17-02-08/59415, 9 July 2020) Ministry of Foreign Affairs of the Russian Federation (№ 2775/датс, 25 June 2020)

Approved by the Joint Planning and Management Committee (JPMC) Number and date of the meeting: Ad-referendum approval on 30 August 2021

Approved by the Joint Cooperation Committee (JCC) Number and date of the meeting: Ad-referendum approval on 17 September 2021

COOPERATION PROJECT ASEAN-RUSSIA. - Project rationale А. Problem analysis The intensification of negative impact of technogenic, environmental, and climatic factors has led the world economy to realize the need to develop a new green economic course based on sustainable activities in various sectors (production, energy, construction, agriculture, etc.). In this regard, cities are the main source of both new risks and opportunities. According to a report by the UN Department of Economic and Social Affairs, for 2018, 55% of the world's population lives in cities, and by 2050 this figure will increase to 68%. Now there are 4.2 billion urban citizens in the world, and in the middle of the XXI century, according to the forecasts, this number will reach 7 billion. According to the UN, 54% of the world's population lives in Asia today. Cities produce 80% of the world’s GDP and most of the financial and intellectual resources are concentrated there. By 2030, at least 13 new megacities are expected to appear in addition to the 28 existing today. The fastest growing urban centers with about a million inhabitants are located in low- and middle-income countries in Asia, which from 2020 to 2050 will become the region with the fastest pace of urbanization. This creates unprecedented problems for the environment and human well-being: cities account for more than 60% of global carbon dioxide emissions that lead to climate change, and cities consume 78% of global energy. ASEAN Member States are also subject to high rates of urbanization - by 2030 the urban population of the countries in the region is expected to increase by another 90 million people. The highest growth is expected in medium-sized cities with a population of 200,000 to 2 million people. According to forecasts, such cities will account for up to 40 percent of the region’s growth. Rapid urbanization in ASEAN Member States may hamper the harmonious development of urban infrastructure. This, in turn, poses problems related to economic inequality, environmental pollution, economic efficiency, health care and food security. Nevertheless, rapid technological development and timely introduction of technological innovations provides cities with numerous opportunities for preparing and solving these problems of urbanization. The challenges of urbanization are also very acute to Russia. According to the UN forecast, by 2050, 75% of Russia's population will be concentrated in cities. The same forecast says that by 2030 Moscow and St. Petersburg, as well as the existing 13 million-plus cities, will remain the most densely populated territories in Russia, while the number of cities with a population from 500 thousand to 1 million people will increase. Such rates of urbanization without the development of new smart technologies for urban management may result in environmental, social and economic problems. To prevent possible threats, investment in new infrastructure and increase in the efficiency of existing systems are required. As stated by the ex-Minister of Construction of Russia Andrei Chibis, 90% of the municipal infrastructure of Russian cities is over 93% loaded. Development of digital urban infrastructure is particularly important, being in line with global development trends outlined by a number of international organizations. Development of smart city technologies and reaction to sustainable development challenges is impossible without proper funding. In this regard, development of trade and investment cooperation between the states of the region, as well as attraction of impact investments for sustainable projects is required. According to estimates from a 2017 study by the United Nations Environment Program and Singapore DBS Bank, ASEAN will need an additional $3 trillion of green investments in infrastructure, renewable energy, energy efficiency, and food and nutrition from 2016 to 2030 to protect resources, people, the environment and the economy from the negative effects of climate change. According to the study, in order to achieve the required indicators, by 2030 the total amount of annual financing of sustainable projects in the region must be increased by 400 percent. Implementation of projects in the field of sustainable development is closely related to matters of monitoring and reporting. One of the most important factors that can encourage investors to fund sustainable projects in the region is increased transparency in impact assessment. This will make it possible to control implementation of projects, as well as monitor their positive environmental and social impact. Thus, the use of Industry 4.0 digital technologies provides opportunity to attract investment flows for the implementation of sustainable projects in the region with lower costs, as well as functionality for monitoring their implementation, which contributes to the achievement of the Sustainable Development Goals by ASEAN Member States . B. Regionality Most of the economic growth in ASEAN is caused by development of urban centers: by 2030, an additional urbanization of 90 million people is expected, and cities with populations of 200,000 to 2 million inhabitants will provide up to 40% of the region’s growth, according to forecasts by Singaporean experts. In this regard, the ASEAN Smart Cities Network initiative was created by the ASEAN Member States to help ASEAN Member States develop and use technological and digital solutions and thereby improve the lives of people in urban and rural areas. In Russia, the national project on smart cities is being developed at the state level with a number of pilot cities participating. The quality of the urban environment, which consists of the communal infrastructure, personal safety of citizens and a number of other factors, including energy efficiency, is now on top of the agenda. Thus, the problem of urbanization is extremely urgent both for ASEAN Member States and Russia, projects are being actively implemented in the field of smart and sustainable cities, which creates the prerequisites for the development of regional cooperation. C. Conference participants ASEAN: 28 participants ASEAN Smart Cities Network National Representatives (10) Investors from ASEAN venture funds (5) - Representatives of GBCI Ventures - Representatives of Thai Venture Capital Association - Representatives of Eastspring Investments - Representatives of Quadria Capital - Representatives of Sunsea Capital Government representatives (10) - Representatives of economic departments - Representatives of construction departments - Representatives of energy departments - Representatives of agricultural departments - Representatives of digital departments - Representatives of the ASEAN Secretariat Russia: 25 participants: - Event organizers (3) - Researchers and experts (2) Government representatives (10) - Representatives of the Ministry of Economic Development (2); - Representatives of the Ministry of Construction (2); - Representatives of the Ministry of Energy (2); - Representatives of the Ministry of Agriculture (2); - Representatives of the Ministry of Communications and Digitalization (2); Representatives of city administrations (10) - Representatives of cities developing projects within the federal project "Smart City" (10) Investors from Russian venture funds (5) - Orbita Capital Partners (1) - AltaIR Capital (1) - Skolkovo Ventures (1) - VEB Ventures (1) - Phystech Ventures (1) International organizations – (7, at own expense) - ITU representative (1) - UN Habitat representative (1) - World Bank representative (1) - Asian Development Bank representatives (2) - UNDP representative (1) - FAO representative (1) Project Partners and Interested Parties from ASEAN Region Representatives of companies, public and research organizations with whom the Project Executor previously interacted and who have the competencies necessary for the implementation of the Project are also expected to participate on a self-expense basis. - Yayasan Kaila Indonesia Berdaya (Indonesia) – in cooperation with this partner, a pilot project may be implemented to demonstrate the functionality of the digital platform. - Singapore Management University (Singapore) - an academic partner who will participate in research for the project. - IPB University (Indonesia) - interested in the potential of financing smart and sustainable agricultural projects using digital financial instruments. - Caraga State University and New Era University (Philippines) - interested in the functionality of the platform for monitoring agricultural projects. - Credit Suisse (Singapore) - a sustainable investment bank in the region with a large agricultural portfolio interested in monitoring capabilities. - Feigin Electric (Thailand, Singapore) - a company developing energy saving solutions, which is interested in the possibility of placing its solution in a “solution bank”. - Green Infrastructure Solutions (Cambodia) – a landscape design and urban planning company dedicated to tackling storm water flooding and urban green spaces. The company is interested in the opportunity to raise funds for the implementation of sustainable projects using the platform, as well as to be listed in the solutions catalog. - World Farmers Organization – an international networking organization representing the interests of farmers. Interested in scaling a pilot project on smart and sustainable agriculture in the SEA region. Selection criteria for project participants: - Funds: operating activities in the SEA region, portfolio includes projects in the field of digitalization and sustainable development, fund size at least $ 1 million. - Institutes: doing research on ASEAN Member States or located in ASEAN Member States, conducting research and working on smart city technology or sustainable development. - Companies: implementing projects in the field of smart cities, sustainable development, digitalization, energy (including renewable energy), agriculture. D. Project beneficiaries Interests of the ASEAN and Russian Federation lie in the development of mutually beneficial partnerships and the exchange of best solutions and practices to solve the pressing issues of urbanization. Implementation of the Project will contribute to the implementation by Russia of the federal program "Smart City", and the implementation of the ASEAN Smart Cities Network initiative. Representatives of small and large businesses, investors, representatives of city administrations and governments of ASEAN Member States and Russia will have an avenue for exchanging views, establishing useful working contacts and concluding beneficial partnerships to strengthen cooperation in the field of smart and sustainable cities. The implementation of the Project will provide support for ASEAN Member States on their national programs for the development of smart cities. In addition, the Project could contribute to increase investment flows in the regional projects that meet the UN Sustainable Development Goals. E. Project Uniqueness The uniqueness of the project primarily lies in its structure, which consists of three complementary stages. The research carried out together with ASEAN experts will identify the best methods and practices for the development of international cooperation. Plus, within the framework of the Project, a specific product will be developed - a digital finance module, that should complement the ASCN online portal and smart and sustainable city investment toolkit that ASEAN is currently developing. At the moment, there are no analogues of such a solution in the world. In addition, the planned international conference will most effectively consolidate the acquired knowledge and developments and introduce them into interaction between the parties. F. Goals, objectives and expected results of the project The main goal of the project is to develop mechanisms to facilitate financing and implementation of technology projects in the field of smart cities and sustainable development of the ASEAN Member States and Russia. Results/ outputs; Indicators; Means of verification. 1. The Study to identify the potential for leveraging digital technologies to foster investment cooperation in innovation for smart and sustainable cities; - Identification of areas of cooperation based on the establishment of direct bilateral and multilateral working contacts between the private and public sectors of the ASEAN Member States and Russia in the field of financing and exchange of innovations for smart and sustainable cities. - Conducting a study with participation of at least 3 experts from Russia and 3 experts from ASEAN Member States . - Preparation of a research report (up to 50 pages).; - Interaction with specialized experts from ASEAN and Russia - Coordinating the work of analysts in a program for Agile project management - Regular online meetings with ASEAN experts. - The research report is published online.. Tasks/activities - Involvement of experts in IT and the ASEAN studies in the research - Involvement of experts from ASEAN Member States in the field of smart and sustainable cities in the research, consultations with partners from the region - Conducting research according to the methods specified in the project stages above - Creation of a research report - Online publication of the research - Distribution of the research results to key stakeholders, such as the ASEAN secretariat, and relevant ministries and departments of ASEAN Member States and Russia (economic, construction, agricultural, environmental, digital and energy departments). The Study will also be distributed to international NGOs, networks and media (magazines, websites, social media) and through Evercity newsletter, which includes contacts of 1000+ of stakeholders in sustainability (such as UN agencies members, CEOs, fund managers, etc.). 2. Creation of innovative tools and approaches to improve the efficiency and transparency of interaction between representatives of city authorities, projects and impact investors from ASEAN and Russia in the field of impact investment and technology exchange.; - Development of an innovative solution in the format of a digital finance module to support the investment cooperation between innovative projects, cities and impact investors. - Implementation of at least three parts of a digital finance module (technical specifications, open-source infrastructure, user interface).; - Coordination of the work of programmers in a program for Agile project management. - Regular online interaction with experts and partners from Russia, ASEAN and international organizations. - Consultation with analysts involved in the research. - Wide participation of representatives of small and large businesses, investors, representatives of cities and governments of ASEAN Member States and Russia in the implementation of the Project.. Tasks/activities - Consultations with key stakeholders from the target countries of the Project - Preparation of a team of 5 IT developers, including a blockchain specialist and a project manager - Implementation of IT development in 3 stages based on the recommendations obtained from the research - Stage 1 - Development of technical specifications and determination of the key parameters of the module - Stage 2 - Development of the open-source digital finance infrastructure - Stage 3 - Development of the user interface for the digital finance module and integration with monitoring tools - Developing the said parts within four months after starting the development - Testing the solution as part of a pilot project in ASEAN - Presentation of the digital finance module and the results of the pilot project at the conference. 3. Pilot Project to promote the introduction of digital technologies in the urban economy of the ASEAN Member States and Russia for the benefit of sustainable development.; - Preparation of feasibility study to assess effectiveness of digital finance module implementation as a part of the study - Conducting at least one digital pilot project in ASEAN Member States - Presentation of the pilot project results for representatives of government agencies and municipalities of ASEAN Member States and Russia (up to 60 conference participants) - Reporting on the results of the pilot project; - Regular online interaction with experts and partners from Russia, ASEAN and international organizations - Personal and online presentation of the pilot results to the key stakeholders. - Report on the pilot project prepared and published in online sources (ASEAN secretariat website, Russian MFA website, etc.). Tasks/activities - Consultations with analysts and experts to develop a pilot project structure - Preparation for the implementation of a pilot project in the ASEAN Member States - Implementation of a pilot project in the field of agriculture / energy / infrastructure - Presentation of the pilot project results at the conference - Preparation of a pilot project report - Sending recommendations to the structures of ASEAN and Russia after the end of the event. 4. Deepening partnerships for innovative development of smart and sustainable cities between ASEAN and Russia.; - Organizing a conference and providing live coverage - participation of representatives of technology companies, investors and city administrators from Russia (up to 15 people), entrepreneurs, investors, representatives of cities of ASEAN Member States and the ASEAN Smart Cities Network (up to 30 people) at the Conference. The total number of participants is up to 100 people. - Up to 20 pitch presentations on the topic of the conference. - Agreements achieved on the development of joint business projects in the field of digital technologies of smart and sustainable cities (at least 1).; - Timely distribution of invitations and formation of delegations. - Active preparation of the pitch session, preparatory work with participating companies. - Advance matchmaking of conference participants that have potential for cooperation. - Report on the conference prepared and published in online sources (ASEAN secretariat website, Russian MFA website, etc.). Tasks/activities - Renting a venue, work with contractors, distribution of invitations, provision of transfer and catering - Ensuring the participation of all partners from the public, private, academic and municipal sectors at the Conference - Preliminary work with innovative companies, foundations and representatives of ASEAN and Russian cities - Organizing the broadcast of the Conference - Organization of a pitch session at the conference - Signing memoranda of intent and other partnership documents during the Conference. 5. Development of a roadmap on measures and methods to support technology exchange and the organization of joint pilot projects in cities of ASEAN Member States and Russia.; - Placing information about the conference on the Internet in Russian and South-East Asian segment (at least 30 web-sites). - Creation of an effective mechanism for establishing direct ties in this area and the development of public-private partnerships, which will be reflected in the Final report on the project. - Preparation of the Final report on the project (which will include recommendatory roadmap) following the results of the Project (up to 30 pages) - Distribution of the document among the specialized structures of ASEAN and Russia; - Active involvement of the Contractor at all stages of the Project - Implementation of all stages of the Project as a single complex. Tasks/activities - Conducting applied research with a practical component - Testing the research results during the pilot project, presentation of the results - Consulting with representatives of business, investment, academic and government circles of ASEAN Member States and Russia - Work on the creation of the Final report - Communication of the results by distributing the Final report among the specialized structures of ASEAN Member States and Russia. G. Management and implementation procedure Organizational matters Allocation of funds, monitoring and assessment of this event is performed in accordance with Guidelines for selection, alignment, financing and reporting of joint activities and cooperation programs of the Russian Federation - ASEAN and Statute of DPFF. The main body for the assessment and coordination of issues related to the conference on the part of ASEAN will be the Working Group on Trade and Economic Cooperation. The ASEAN Secretariat will assist in evaluating the project proposal and coordinate interaction between the ASEAN and Russian side. Participants from the ASEAN Member States and Russia will be determined by the ASEAN Secretariat and the Ministry of Economic Development of Russia. The final agenda of the conference and the date of its holding will be specified jointly by the ASEAN Secretariat and the Russian side. ASEAN Senior Officials’ Meeting (SOM) as the sponsoring body of this proposed project will provide guidance on the implementation of the project, as necessary. As this project seeks to engage the ASCN, therefore, the ASCN will also be consulted. All progress reports will be addressed and submitted to ASEAN SOM and ASCN, as necessary. ASEAN Connectivity Division will coordinate with relevant ASEC divisions and facilitate the consultation process with ASEAN SOM and ASCN members. The implementing agency is Evercity LLC, an organization that will be responsible for receiving funds and carrying out activities from the Russian side. It will coordinate the research, develop the digital finance module, implement a pilot project and organize a conference. The core team of Evercity will consist of no less than 10 people and include: Managing partner, project operational manager, marketing manager, engagement manager, designer, 5 IT specialists and ad-hoc analysts and editor. The implementing agency and its team earlier have received the award ‘Best ecosystem solution’ by the International Telecommunication Union (ITU) and presented it at UNFCCC COP 25. The project initiator (Ministry of Economic Development of the Russian Federation, Department of Multilateral Economic Cooperation and Special Projects) will coordinate and implement the overall project and the concluding event. It will allocate 2 people of personnel (not covered by the project’s budget). H. Monitoring and Evaluation Procedure The project will be monitored by the project team in close collaboration with the ASEAN Secretariat. The project team will develop questionnaires to be filled out by the project participants at the end of the Conference. Performance indicators also include the number of conference participants, the number of innovative projects that participated in the pitch session, the number of downloads of the final document, the number of signed letters of intent, the number of mentions in the media. I. Indicative work plan Project schedule - see Appendix 1. Preliminary conference program: Day 1. High level policy day. 09:00-10:00; Opening ceremony. 10:00-11:00; Presenting results of the research. 11:00-12:00; Presenting the digital finance module. 12:20-13:00; Plenary Session: Topical Issues of Smart and Sustainable Cities in ASEAN Member States and Russia Participants: Representatives of ministries, departments, city authorities and international organizations.. 14:00-15:40; Breakout Session: Technology Exchange to Achieve the SDGs Participants: Representatives of ASEAN and Russian government agencies, international organizations; Breakout session: Funding and support measures for the development of Industry 4.0 & urban infrastructure Participants: Representatives of ASEAN and Russian government bodies, business, international organizations; ASEAN Smart Cities Network and Russian Smart Cities interaction session.. 16:00-17:40; Breakout session: Agriculture and food security Participants: Representatives of ASEAN and Russian government agencies, international organizations; Breakout Session: Industry & Infrastructure Participants: Representatives of government agencies and cities of ASEAN and Russia; Breakout session: Energy Participants: Representatives of ASEAN and Russian government agencies. After 18:00; Networking session. Day 2. Business & Innovation day. 9:30-11:00; Breakout session: Agriculture and food security; Breakout Session: Industry & Infrastructure; Breakout session: Energy. 11:20-13:00; Breakout session: Fostering technology exchange and investment cooperation between ASEAN and Russia.; Pitch session. 14:00-15:40; Opportunities for business cooperation between ASEAN Member States and Russia; Pitch session. 16:00-16:25; Signing agreements; Summing up the results. 16:40-17:40; Closing ceremony.. J. Interdisciplinary matters: The Project addresses the issues of enhancing strategic cooperation between ASEAN and Russia to create an effective system for strengthening socio-economic and technological potential of countries, promoting transfer of technologies and their commercialization. The Project is aimed at stimulation of investment cooperation, public-private partnerships and increasing investment flows in projects in the field of smart and sustainable cities between ASEAN and Russia. The project is also aimed at supporting the national sustainable development strategies of the participating states, as well as promoting greener and more sustainable development of the energy, infrastructure and agriculture sectors. The Project promotes the development and implementation of the latest digital innovations in the urban economy of the ASEAN Member States and Russia. Upon completing the project, its key components will be sustained further. The results of the research will be sustained by creation of a profiled think-tank of experts on Smart and Sustainable Cities and Technologies which will benefit to further deepening of cooperation in these spheres. The results of the pilot project will be used to further improve the digital finance module and use it for similar projects in the region. The digital finance module will be managed by the Evercity company and can be tailored to the needs of its users (banks, development finance institutions, companies and city administrations of ASEAN Member States). The results of the conference are expected to set the basis for extensive cooperation in smart sustainable city innovations between ASEAN and Russia. K. Risk assessment To assess risks, the method of alternative scenarios was used; regular monitoring of the situation in the region is ensured in a view of the spread of the COVID-19 epidemic. Risk; Probability and prevention.. Change in the timeline; Probable. Despite the fact that the project team has a sufficient number of administrative staff to complete the project on time, in a view of the spread of the COVID-19 in Russia and the world, the project implementation timeline may shift by 2-4 months.. Delay in signing the contract between the ASEAN Secretariat and the Contractor; Unlikely. The contractor and initiator of the project will maintain close contact with the ASEAN Secretariat and the relevant government agencies for the prompt execution of the necessary project documentation.. Insufficient number of conference participants (less than 50 people); Potential participants will receive invitations, as well as information about the place and time of the Conference in advance. The contractor will monitor and provide support to each of the participants with the assistance of the ASEAN Secretariat.. Failure to finalize the practical part of the study - digital finance module; Unlikely, as the team has extensive experience in the implementation of complex IT projects, which will allow the development to be completed on time. Thus, all these digital solution parts will be successfully functioning by the time of the conference.. Inability to raise funds for the further development of the digital finance module after the Project; Unlikely, as the conference will host venture fund representatives, with whom a preliminary discussion on cooperation under this project will be held. In addition, the digital finance module has a commission-based financial model, which provides an opportunity to raise funds for its operation. There will be preliminary agreements with clients for using the digital finance module, and the pilot project will help to demonstrate all the functionality with real market participants. The module is also gaining particular relevance in a view of the spread of the COVID-19 pandemic, since it can be used to monitor projects to eliminate the negative consequences of the pandemic.. L. Additional funding Funding for the participation of representatives of federal executive bodies, as well as other interested departments will be carried out within the allocations provided for these bodies for the corresponding year. Funding for the participation of representatives of innovative companies interested in participating and approved by the organizers, but not included in the preliminary list of participants in the Pitch session within the framework of the Conference, is carried out from the budgets of these companies. M. Budget and funding plan The necessary expenses for the conference are presented in the form of a table in Appendix 2. Source: ASEAN-Russian Federation Dialogue Partnership Financial Fund. N. Annex Indicative work plan. Budget proposal. O. Finalization of the project Finalization of the project proposal is carried out in accordance with the procedure outlined in the Guidelines for the selection, approval and financing of joint activities and programs of Russia-ASEAN cooperation and the Organizational Scheme for the selection, approval and financing of joint projects carried out at the expense of the ASEAN-Russian Federation Dialogue Partnership Financial Fund. P. Project Initiator and Coordinator Ministry of Economic Development of the Russian Federation, Department of Multilateral Economic Cooperation and Special Projects Contact person: Natalia Stapran, Director of the Department E-mail: Stapran@economy.gov.ru _________________________________________________________________

Annex 1. Indicative workplan.

Annex 2.  Budget proposal.

https://sustainabledevelopment.un.org/content/documents/28341101118aseanprogresstowadssustainabledevelopmentgoals.pdf

https://asean.org/storage/2019/02/ASCN-Concept-Note.pdf

https://sustainabledevelopment.un.org/partnership/?p=29570

https://asean.org/storage/2019/01/ASEAN-Digital-Integration-Framework.pdf

https://asean.org/storage/2016/09/Master-Plan-on-ASEAN-Connectivity-20251.pdf

https://meteoinfo.ru/images/media/books-docs/klim-riski-2017.pdf

https://www.austausch.org/files/DRA/Publikationen/Nachhaltige_Entwicklung_in_Russland.pdf

https://asean.org/comprehensive-plan-action-promote-cooperation-association-southeast-asian-nations-russian-federation-2016-2020/

https://www.asean.org/storage/2016/05/Sochi-Declaration-of-the-ASEAN-Russia-Commemorative-Summit-Final.pdf

https://asean.org/storage/2018/11/ASEAN-Russia-Joint-Statement.pdf

http://www.rsbctrade.com/exhibition-of-russian-technologies/

http://www.thaiembassy.org/moscow/en/news/8036/101151-Royal-Thai-Embassy-in-Moscow-participated-in-the-I.html

http://thailand.mid.ru/en/key-issues/5152-fchdg-1412

http://www.fao.org/e-agriculture/news/e-agriculture-action-blockchain-agriculture

http://www.oecd.org/cfe/regional-policy/Smart-Cities-FINAL.pdf

http://www3.weforum.org/docs/WEF_Windows_of_Opportunity.pdf

https://www.asean.org/storage/images/2015/October/ASEAN-Regional-Guidelines-on-Promoting-CSA-Practices/ASEAN%20Regional%20Guidelines%20on%20Promoting%20CSA%20Practices-endorsed%2037th%20AMAF.pdf

https://population.un.org/wup/

https://unu.edu/projects/smart-cities-for-sustainable-development.html#outline

https://www.un.org/en/climatechange/cities-pollution.shtml

https://www.clc.gov.sg/docs/default-source/books/book-asean-smart-cities-network.pdf

https://asean.org/storage/2018/11/ASEAN-Sustainable-Urbanisation-Strategy-ASUS.pdf

https://population.un.org/wup/Country-Profiles/

http://gorodsreda.ru/upload/iblock/00e/prezentatsiya_umnyy-gorod_-14.03.pdf

https://wedocs.unep.org/bitstream/handle/20.500.11822/22284/Green_Finance_ASEAN.pdf?sequence=1&isAllowed=y

https://asean.org/concept-note-of-the-asean-smart-cities-network/

http://gorodsreda.ru/upload/iblock/00e/prezentatsiya_umnyy-gorod_-14.03.pdf

Agile is a process by which a team can manage a project by breaking it up into several stages and involving constant collaboration with stakeholders and continuous improvement and iteration at every stage.