# Detailed Action Plan and Timeline for ASEAN Digital Capacity Building for Smart Cities: ASEAN Chief Smart City Officers (ASEAN-CSCOs)

## 1. Detailed Action Plan

### 1.1 Management Arrangements

- Objective: Establish a robust project management framework to ensure alignment with goals and timelines.

- Details:

  - Formation of Project Team (Feb 2025): A team comprising a project manager, technical experts in smart city technologies, and administrative staff will be established. The project manager will oversee coordination, budgeting, and reporting.

  - Bi-Weekly Coordination Meetings (Feb–Dec 2025): Held virtually with representatives from ADSOM, ASCN, and MPAC Sectoral Body. Agenda includes progress updates, issue resolution, and activity planning. Minutes will be circulated within 3 days post-meeting.

  - Quarterly Review Meetings (Apr, Jul, Oct, Dec 2025): Conducted with ASEAN member state representatives to review milestones, gather feedback, and adjust plans. Reports submitted to ADGSOM within 7 days post-meeting.

- Participants: Project team, ADSOM, ASCN, MPAC representatives, and selected ASEAN member state officials (approx. 15–20 per meeting).

- Outcome: Transparent project execution, stakeholder alignment, and timely issue resolution.

- Follow-Up: Monthly progress reports submitted to ADGSOM, with actionable feedback incorporated into subsequent plans.

### 1.2 Online Preparatory Engagements

- Objective: Customize workshop content to address specific urban challenges and set clear learning objectives.

- Details:

  - Webinar Series (Mar–May 2025, 3 sessions):

    - Participants: 30–35 policymakers, urban planners, and technologists from ASEAN member states. Selection criteria include:

      - Role in smart city planning or implementation.

      - Representation from diverse ASEAN cities (urban/rural, ASCN/non-ASCN).

      - Commitment to attend follow-up workshops.

    - External Invitees: Private sector experts from Thailand Digital Catalog (e.g., tech firms specializing in IoT, e-governance) and ASEAN Smart Cities Network mentors (2–3 per session).

    - Preparation: Participants submit a 1-page brief on their city’s smart city challenges (e.g., digital infrastructure gaps, citizen engagement issues) 10 days prior.

    - Agenda:

      - Session 1 (Mar): Smart city frameworks and regional challenges.

      - Session 2 (Apr): Technology integration and public-private partnerships.

      - Session 3 (May): Needs assessment results and workshop preview.

    - Format: 2-hour virtual sessions via Zoom, with breakout rooms for focused discussions.

  - Needs Assessment Surveys (Mar 2025): Online surveys sent to participants post-Session 1 to identify priority areas (e.g., e-services, flood management).

- Outcome: Tailored workshop content, stakeholder buy-in, and baseline data for capacity gaps.

- Follow-Up: Summary report circulated within 5 days post-webinar. Feedback integrated into workshop design.

### 1.3 Experimental Workshop in Nakhon Si Thammarat

- Objective: Provide hands-on exposure to successful smart city initiatives.

- Details:

  - On-Site Workshop (Jul 2025, 3 days):

    - Participants: Same 30–35 policymakers/planners from webinars, plus 5 local officials from Nakhon Si Thammarat.

    - Selection Criteria: Confirmed attendance from webinar series and submission of city challenge brief.

    - External Invitees: 2–3 private sector speakers (e.g., developers of Nakhon’s e-service platform) and 1 ASEAN Secretariat representative.

    - Agenda:

      - Day 1: Presentations on Nakhon Si Thammarat’s smart city model (citizen e-services, flood prevention).

      - Day 2: Field visits to smart city projects (e.g., flood monitoring systems, digital service kiosks).

      - Day 3: Group exercises to draft city-specific smart city plans, facilitated by technical experts.

    - Preparation: Participants receive a pre-workshop handbook draft and case study summaries 2 weeks prior.

  - Logistics: Venue, meals, and materials funded by Thailand (USD 5,000). Travel/per diem for 9 participants and 1 speaker funded by AICTF (USD 11,700).

- Outcome: Practical skills in smart city implementation, actionable city plans, and strengthened regional networks.

- Follow-Up: Post-workshop survey conducted on-site. Results summarized in a report to ADGSOM within 10 days.

### 1.4 Online Collaboration Platform and Handbook Production

- Objective: Sustain engagement and provide a lasting resource for smart city development.

- Details:

  - Digital Forum Launch (Aug 2025): A cloud-based platform (e.g., Microsoft Teams) for participants to share updates, challenges, and solutions.

    - Participants: Open to workshop attendees, with invitations extended to ASCN cities and Thailand Digital Catalog firms.

    - Moderation: Managed by depa’s technical team, with monthly discussion prompts (e.g., scaling e-services).

  - Handbook Development (Mar–Sep 2025):

    - Content includes best practices (e.g., Nakhon Si Thammarat case), frameworks for citizen-centric design, and financing models.

    - Draft reviewed by ASCN experts in Jun 2025; finalized by Sep 2025.

    - Distributed digitally to all ASEAN member states and promoted at regional events.

  - Monthly Progress Reports (Feb–Dec 2025): Detail activities, challenges, and next steps. Submitted to ADGSOM within 5 days of month-end.

- Outcome: Continuous knowledge exchange, a widely adopted handbook, and sustained regional collaboration.

- Follow-Up: Platform usage analytics reported quarterly. Handbook feedback collected via surveys in Nov 2025.

## 2. Detailed Timeline

| Month | Activity | Tasks |
| --- | --- | --- |
| Jan | Pre-Planning | Finalize project team roles, secure approvals, and set up platforms. |
| Feb | Management Arrangements, Online Engagements | Form project team, hold first coordination meeting, launch webinar invites. |
| Mar | Online Engagements, Handbook Development | Webinar 1, needs assessment surveys, start handbook drafting. |
| Apr | Management Arrangements, Online Engagements | Webinar 2, quarterly review meeting, continue handbook work. |
| May | Online Engagements | Webinar 3, finalize workshop agenda based on survey results. |
| Jun | Management Arrangements, Handbook Development | Coordination meeting, handbook draft review with ASCN experts. |
| Jul | Nakhon Si Thammarat Workshop | Conduct 3-day workshop, field visits, and group exercises. |
| Aug | Online Collaboration Platform | Launch digital forum, share workshop outcomes, continue handbook. |
| Sep | Handbook Production | Finalize and distribute handbook, coordination meeting. |
| Oct | Management Arrangements | Quarterly review meeting, platform moderation, progress report. |
| Nov | Online Collaboration Platform | Collect handbook feedback, share platform analytics. |
| Dec | Project Wrap-Up | Final evaluation, submit completion report to ASEAN Secretariat. |

## Notes

- PPT Submission: A PowerPoint presentation summarizing the action plan, timeline, and expected outcomes will be prepared by late March 2025, as requested.

- Budget Alignment: Activities align with the proposed budget (USD 14,800 AICTF, USD 5,000 Thailand).

- Sustainability: The digital forum and handbook ensure long-term impact, with ASCN networks fostering ongoing collaboration.