| Remark: To seek input from MPAC Sectoral Body ASEAN Cooperation Project Proposal For assistance on how to complete this template, please refer to the “ASEAN Cooperation Projects Design and Management Manual”, which can be downloaded at http://asean.org/resource/asean-project-templates/. |  |  |  |
| --- | --- | --- | --- |
| 1. Project Details |  |  |  |
| Proposal Identification Code: (to be completed by the ASEAN Secretariat) |  |  |  |
| Project Title: ASEAN Digital Capacity Building for Smart Cities: ASEAN Chief Smart City Officers (ASEAN-CSCOs) |  |  |  |
| Brief Project Description – 300 words max: This project is designed to enhance the digital capacity of ASEAN policymakers and implementers, focusing on the development and implementation of smart city strategies that foster digital inclusivity and sustainability across the region. Building on the progress initiated in AIM 2020 and aligned with EA7.4 of ADM2025, this initiative supports the Masterplan on ASEAN Connectivity 2025 (MPAC2025). Through a series of practical, hands-on workshops and the creation of an online collaborative platform, participants will gain the necessary tools and insights to develop citizen-centric smart city initiatives. Key elements of the project include developing a comprehensive handbook for smart cities, which will serve as a critical resource for policymakers and urban planners throughout ASEAN. The handbook will compile best practices, case studies, and strategic frameworks, providing a step-by-step guide to navigating the complexities of smart city development. Recognizing the importance of diverse perspectives, the project will actively involve the private sector in workshops to share global tech transformation experiences and best practices. This collaboration will ensure that the latest technological innovations and private sector expertise are integrated into public sector planning and implementation. The proposal also considers the diverse needs and contexts of stakeholders across the ASEAN region, ensuring that the project is adaptable and relevant to various local conditions. By empowering policymakers with practical skills and fostering regional collaboration, this project aims to significantly advance the smart city agenda in ASEAN, promoting sustainable urban development and improving the quality of life for citizens across the region. |  |  |  |
| Recurring Project: Yes No √ If Yes, Previous Project Identification Code: Indicate if the proposed project is part of a series of projects that involve similar objectives, outputs, and activities. |  |  |  |
| Project Classification: Indicate the Scope and Pillar Scope: Single Sector Cross-Sector √ |  |  |  |
| Pillar: | (Main) Blueprint: (Main) Characteristic: Action Line(s): Action(s): | Connectivity √ Linkage: Strategy: Key Action(s): | IAI |
| Information below to be completed by the ASEAN Secretariat: Nature of Confidence Building Cooperation: Harmonisation Special Assistance Joint Effort Regional Integration / Expansion Type of Policy Initiative Intervention: Establishment of Institutional Mechanisms Human Capacity Building |  |  |  |
| Project Duration: < 6 months 6-12 months> 12 months √ Proposed Commencement Date: January 2025 Proposed Completion Date: December 2025 A project is considered to have commenced on the date that the Proponent or IA is informed of the approval and upon receipt of the first tranche of funds disbursement. A project is considered to have been completed when the project completion report and unspent balance, if any, has been received and verified by the ASEAN Secretariat. The proponent is required to submit the project completion report, which comprise of narrative and financial report, within 60 days after the project is fully implemented. The report templates are available at http://asean.org/resource/asean-project-templates/ |  |  |  |
| Participating ASEAN Member States: All If not all (or not all in the same way), please indicate reason: ### ASEAN cooperation projects are expected to involve the participation of every ASEAN Member State. If a project involves the participation of every ASEAN Member State but in different ways (e.g., through different levels of assistance) or does not involve every ASEAN Member State, please indicate the reason. |  |  |  |
| Sponsoring ASEAN Body Sectoral Committee/Main Body: Meeting Number/Date: / dd.mm.yyyy Working Group/Sub-Committee: Meeting Number/Date: / dd.mm.yyyy The proponent may consult with ASEAN Secretariat to identify the most appropriate sponsoring ASEAN Body for the project. |  |  |  |
| Proponent’s Name and Address: Dr Non Arkaraprasertkul Digital Economy Promotion Agency (depa) of Thailand 80 Soi Ladprao 4 Jatujak Bangkok 10900 Thailand Implementing Agency’s Name and Address (if different from above): Contact Person and Contact Details: |  |  |  |
| Date of Proposal Submission: dd.mm.yyyy |  |  |  |
| Proposed Funding Source(s): Consult with the ASEAN Secretariat, relevant ASEAN Sectoral Committee, or relevant ASEAN Body to identify a proposed funding source. |  |  |  |
| Proposed Project Budget (total in USD): 1. Funding from ASEAN ICT Fund: 14,800 USD 2. Funding from Thailand: 5,000 USD Total: 19,800 USD |  |  |  |
| Information below to be completed by the PCPMD of the ASEAN Secretariat Recommendation of the ASEAN Secretariat Meeting No./Date; :; / dd.mm.yyyy. Action; :; Endorsed; Not Endorsed. |
| Approval of Committee of Permanent Representatives to ASEAN (CPR) Meeting No./Date; :; / dd.mm.yyyy. Action; :; Endorsed; Not Endorsed. |
| - Project Justification, Regionality and Beneficiaries – 600 words max (For more details, see the “ASEAN Cooperation Projects Design and Management Manual”) - Current Problem: The ASEAN region is grappling with rapid urbanization, presenting significant challenges in sustainable growth and digital transformation. Policymakers and implementers across ASEAN lack the necessary capacity to effectively integrate smart city solutions that can address these challenges. Despite notable successes in countries like Thailand, such as the smart city initiatives in Nakhon Si Thammarat, a region-wide, cohesive approach is essential to amplify these successes and ensure sustainable urban development. The need for enhanced digital infrastructure, governance, and public-private collaboration remains critical to achieving these goals. - Regionality: The issues of urbanization and digital transformation are ubiquitous across all ASEAN member states, necessitating a coordinated regional response. This project builds on the progress initiated in AIM 2020, linking directly to EA7.4 of ADM2025, and aligns with the strategic goals of the Masterplan on ASEAN Connectivity 2025 (MPAC2025). By fostering regional cooperation and knowledge exchange, this project aims to provide a unified approach to developing citizen-centric smart cities throughout ASEAN. - Project History: Since the ASEAN Secretariat endorsed the ASEAN Smart Cities Network (ASCN) in Singapore during the nation’s chairpersonship in 2018, Thailand has been at the forefront of promoting small city initiatives. Over the past seven years, Thailand has built capacity for key decision-makers and operators, including Chief Smart City Officers (CSCOs), Smart City Leadership (SCL), Smart City Ambassadors (SCAs), Smart City Data Officers (SCDOs) and Smart City Officers (SCOs). Despite the pandemic, more than 1,000 officers and participants have been trained, leveraging online platforms to continue these efforts. These initiatives highlight Thailand's commitment to driving smart city development through both policy and implementation. This proposal seeks to build on these efforts by establishing a comprehensive, region-wide capacity-building program. Drawing from successful projects, such as those in Nakhon Si Thammarat, the project will provide practical, hands-on workshops and develop a collaborative platform for continuous engagement. Moreover, it will involve digital providers listed in Thailand Digital Catalog, enhancing public-private partnerships and integrating advanced digital solutions into the public sector. This approach ensures that the project is both innovative and grounded in proven success models. - Beneficiaries: - Direct Beneficiaries: Approximately 30-35 policymakers, urban planners, and technologists from ASEAN member states will directly benefit from this project. They will receive practical training and exposure to successful smart city practices, equipping them with the skills needed to implement these solutions in their respective countries. - Indirect Beneficiaries: The indirect beneficiaries include the citizens and businesses within the participating smart cities, potentially impacting millions of people. Improved urban governance and enhanced digital services, the citizens and businesses within the participating smart cities will elevate the quality of life, promote economic growth, and ensure more efficient public services. |  |  |  |
| - Project Results Overall Objective (impact) The intended physical, financial, institutional, social, environmental, or other high-level development results, e.g., at the ASEAN Blueprint level, to which a project is expected to contribute.. Project Objective (outcome) - Equip ASEAN policymakers with practical skills for smart city development. - Produce a comprehensive handbook for citizen-centric smart city initiatives.; Indicators (to measure project achievements - Number of workshops conducted, and participants trained. - Number of pilot projects launched within 12 months post-workshop. - Distribution and adoption of the Handbook for Citizen-Centric Smart Cities.; Sources/Means of Verification - Workshop attendance records and participant feedback. - Reports on pilot project implementations. - Distribution logs and usage surveys for the handbook.; Risk/ Assumption - Risks: Limited participation due to travel restrictions, insufficient engagement from stakeholders. - Assumptions: Strong interest and commitment from ASEAN member states, effective collaboration with MPAC Sectoral Body.. Outputs (direct project results) - Conducted workshops and training sessions. - Published and distributed handbook.; Indicators (to measure project achievements) - Workshop feedback and participant competency evaluations. - Network activity metrics and collaboration records. - Handbook distribution and usage reports.; Sources/Means of Verification - Participant surveys and competency assessments. - Network interaction logs and meeting minutes. - Handbook distribution lists and user feedback.; Risk/ Assumption - Risks: Disruptions due to unforeseen circumstances. - Assumptions: Continued support from ASEAN bodies and participating cities.. Main Activities: - Q2/2025: Online Preparatory Engagements - Q3/2025: Experiential Workshops in Nakhon Si Thammarat - Q4/2025: Online Collaborative Platform and Handbook Production. |
| - Project Management Arrangements – 600 words max - Management Arrangements The project will be managed by the Digital Economy Promotion Agency (depa) of Thailand. A dedicated project team will be formed, consisting of project managers, technical experts, and administrative staff. The project manager will be responsible for overall project coordination and management, ensuring that all activities are aligned with the project goals and timelines. Regular updates and reports will be provided to ADGSOM to maintain alignment with regional goals and ensure transparency. The project team will hold bi-weekly coordination meetings to track progress, address any issues, and make necessary adjustments. These meetings will include representatives from ADSOM and other related sectoral bodies such as ASCN and the MPAC Sectoral Body to ensure that regional perspectives and priorities are integrated into the project implementation. Additionally, quarterly review meetings will be conducted with key stakeholders, including representatives from ASEAN member states, to provide updates on project progress and gather feedback. These management arrangements are to drive the relevant Desired Outcome of ADM2025, i.e., the delivery of trusted digital services and the prevention of consumer harm, to increase in the quality and use of e-government services, and to facilitate co-creation of digital services to connect businesses and facilitate cross-border trade. This project will meet the Enabling Action of ADM2025 in the following way: by enhancing online security technologies to build trust across critical sectors like finance, healthcare, education, and government; improving regional coordination of computer incident response; boosting government productivity through internal ICT and e-services adoption; and ensuring compliance with ASEAN trade agreements to secure the benefits of telecommunications and e-commerce. These actions will collectively strengthen digital security, foster regional cooperation, and promote the safe expansion of digital services across ASEAN member states. This will align the project more closely with existing frameworks and strategic goals. - Human Resource Inputs - Project Manager: The Project Manager will be responsible for the overall coordination and management of the project. This includes developing detailed project plans, managing budgets, coordinating with stakeholders, and ensuring that project deliverables are met on time and within scope. - Workshop Facilitators: A team of experts in smart city development and digital governance will facilitate the workshops. These facilitators will provide technical training, share best practices, and guide participants through hands-on activities. - Technical Experts: Technical experts will be involved in the development of the Handbook for Citizen-Centric Smart Cities and will provide ongoing support to workshop participants. These experts will also assist in the evaluation of pilot projects and the implementation of digital solutions. - Administrative Support: Administrative staff will handle logistics, communication, and documentation. This includes organizing workshops, managing participant registrations, coordinating travel and accommodation, and maintaining project records. - Monitoring and Evaluation Arrangements Monitoring and evaluation (M&E) are critical components of the project to ensure that activities are on track and objectives are being met. The target group for the feedback surveys conducted after each workshop are the participants who are key decisionmakers from the respective ASEAN countries. The M&E plan will include the following components: - Regular Progress Reports: - Monthly progress reports will be prepared by the project team, detailing activities completed, challenges encountered, and plans for the upcoming month. - These reports will table to ADGSOM to ensure transparency and accountability. - Participant Feedback: - Surveys will be conducted after each workshop to gather feedback from participants. This feedback will assess the effectiveness of the training, the relevance of the content, and the overall satisfaction of the participants. - Focus group discussions will be held with a subset of participants to gather more in-depth insights and recommendations. - Milestone Assessments: - Key project milestones will be identified, and progress against these milestones will be assessed quarterly. This will include evaluating the development and distribution of the Handbook for Citizen-Centric Smart Cities and the implementation of pilot projects. - Milestone assessments will be reviewed during the quarterly review meetings. - Final Evaluation: - A comprehensive final evaluation will be conducted at the end of the project. This evaluation will measure the overall impact and outcomes against the project objectives. - Measurable outputs are evaluated according to the S.M.A.R.T. (Specific, Measurable, Achievable, Relevant, Time-bound) framework. In this case, the number of workshops (2) and training sessions (5) on individual topics relevant to the concept and practice of citizen-centric smart city development are planned for the participants throughout the preparation period, on-site training as well as post-course monitoring of this CSCO courses. These topics include human-centric approach to design, financing smart cities, purposeful technology and result-oriented solution co-creation, leadership’s roles in smart city promotion, and management model for smart solutions. - The final evaluation will include an analysis of data collected through surveys, interviews, and project records. It will assess the improvement in digital governance skills among participants, the effectiveness of the regional network for smart cities, and the adoption and utilization of the handbook. - The findings of the final evaluation will be documented in a detailed report, which will be submitted to ADGSOM, including all stakeholders. - Continuous Improvement: - The project team will use the feedback and insights gathered from the M&E activities to make continuous improvements to the project. This iterative approach will ensure that the project remains responsive to the needs of the participants and the evolving context of smart city development in ASEAN. - By implementing a robust management structure and comprehensive M&E plan, the project will ensure effective coordination, transparent reporting, and continuous improvement, ultimately achieving its goals of enhancing digital capacity and promoting sustainable urban development in ASEAN. |  |  |  |
| - Project Sustainability – 300 words max The sustainability of the project outcomes is paramount to ensuring lasting impact beyond the project’s duration. The key elements that will contribute to the project's sustainability include the enhancement of the ASEAN Smart Cities Network (ASCN) operations, the distribution and utilization of the Handbook for Citizen-Centric Smart Cities, ongoing capacity-building activities, and strong public-private partnerships. - Enhancement of the ASCN Operations and Regional ASCN Networks: The project will enhance the operation of the ASCN by establishing regional networks for cities across ASEAN. These networks will enable cities that are not ASCN members to join forces with ASCN cities, fostering collaboration and mutual support. ASCN cities can serve as incubators, helping to transform nearby cities within their regions. For example, Nakhon Si Thammarat and Phuket (an ASCN city) can team up to create a hub for promoting smart city initiatives in southern Thailand. This approach aligns with the ASEAN Secretariat's mission to promote regional integration and sustainable urban development. - Handbook for Citizen-Centric Smart Cities: The Handbook for Citizen-Centric Smart Cities will serve as a comprehensive resource for policymakers and urban planners across ASEAN. It will provide practical guidelines, case studies, and strategic frameworks that can be adapted to various local contexts. The handbook will be widely distributed and promoted through digital platforms and regional events, ensuring that it remains a relevant and accessible tool for guiding smart city development. - Ongoing Capacity-Building Activities: To reinforce the skills and knowledge gained during the project, depa will organize follow-up training sessions, workshops, and webinars. These activities will be tailored to address emerging trends and technologies in smart city development. By providing continuous learning opportunities, the project will help build a cadre of well-equipped professionals capable of driving sustainable urban development. - Public-Private Partnerships: Engaging digital providers listed in Thailand Digital Catalog will strengthen public-private partnerships. These collaborations will ensure that innovative solutions and technologies are integrated into public sector projects, enhancing the quality and sustainability of smart city initiatives. The involvement of private sector experts will also provide ongoing support and mentorship to public sector officials. - Policy Integration and Local Ownership: The project will work with local governments to integrate smart city strategies into their urban planning and development policies. By aligning project activities with existing policy frameworks and development plans, the project will foster local ownership and ensure that smart city initiatives are sustained and scaled over time. By focusing on these key elements, the project will create a robust foundation for sustained impact, ensuring that the benefits of digital capacity-building and smart city development continue to enhance urban governance and quality of life in ASEAN cities well into the future. |  |  |  |
| - Gender And Other Cross Cutting Issues – 300 words max - Gender - The project will ensure equal participation opportunities for men and women. Efforts will be made to address gender-specific needs and encourage active involvement of women in smart city initiatives. - Other Cross Cutting Issues - The project will consider environmental sustainability by promoting green smart city practices. Inclusion of marginalized groups, such as the elderly and people with disabilities, will be prioritized in the design and implementation of smart city solutions. |  |  |  |
| - Potential Risks Outline all significant potential external risks or threats in the Project Results along with corresponding mitigation strategies using the following table: Risk / threat; Mitigation strategy. Limited participation due to travel restrictions; Offer virtual participation options. Insufficient engagement from stakeholders; Early and continuous stakeholder engagement and communication. |
| _______________ Annex 1 – Budget Proposal: ASEAN ICT Fund Expense Category; Description; Estimated Cost (USD). Hosting Expense; 5,000. Expert/Speaker; Honorarium $500 + Per Diem (3 days) $600 + Airfare $700; 1,800. AMS traveling expense; For 9 AMS and 1 ASEC (Air tickets $700 + $600 per diem x 3 days); 13,000. Total:; 19,800. |
| Annex 2 – Indicative Work Plan Activity; Timeframe. Online Preparatory Engagements; Q2/2025. Experiential Workshops in Nakhon Si Thammarat; Q3/2025. Online Collaborative Platform and Handbook Production; Q4/2025. |
| Annex 3 – Notation on Additional Supporting Documents List additional supporting documents that will submitted with the project proposal that will enhance understanding of the proposal and its overall strategy, e.g., reports, memoranda of understanding, etc. |  |  |  |