## 01-Budget
Project Title : |  | ASEAN Digital Capacity Building for Smart Cities: ASEAN Chief Smart City Officers (ASEAN-CSCOs)
Implementing Agency : |  | depa Thailand
Duration/Period : |  | 2025 (the commencement date depends on the approval) 12 Months
ADM2025 |  | E.A. 7.4 of ADM2025
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Budget Line | Description |  | Unit Cost (USD) | Quantity 1 | Unit 1 | Package | Unit 2 | Total Cost (USD) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
I. PROGRAMME/ACTIVITY COST
A. Workshop participants (AICTF)
A.1 | Air travel |  | 700 | 9 | Person | 1 | time | 6300 | bar: 7 Jul to 9 Sep
A.2 | per diem |  | 200 | 9 | Person | 3 | day | 5400 | bar: 7 Jul to 9 Sep
Total Budget for Workshop | [7 empty] | 11700
B. Speaker (AICTF)
B.1 | Speaker |  | 500 | 1 | Person | 1 | time | 500 | bar: 7 Jul to 9 Sep
B.2 | Air Travel |  | 700 | 1 | Person | 1 | time | 700
B.3 | per diem |  | 200 | 1 | Person | 3 | day | 600
Total Budget for Speaker | [7 empty] | 1800
C. ASEC (AICTF)
C.1 | Air Travel |  | 700 | 1 | Person | 1 | time | 700 | bar: 7 Jul to 9 Sep
C.2 | per diem |  | 200 | 1 | Person | 3 | day | 600
Total Budget for ASEC | [7 empty] | 1300
SUB TOTAL OF PROGRAMME COST (I) | [7 empty] | 14800
II. OPERATIONAL COST
C. Hosting Forum (Self Funded by TH)
C.1 | Meeting Packages/ Meals/ Field Trip/ Workshop Materials/ Handbook Production |  | 5000 | 1 | Lumpsum | 1 | time | 5000 | bar: 7 Jul to 12 Dec
Total Budget for Hosting | [7 empty] | 5000
SUB TOTAL OF OPERATIONAL COST (II) | [7 empty] | 5000
TOTAL (I + II) | [7 empty] | 19800
AICTF | 14800 |  | 14800
Self Funding | 5000 |  | 5000
| 19800 |  | 19800
Note on I12: Lenovo: we have to add 1 more for ASEC

## 02-Workplan
Project Title : | ASEAN Digital Capacity Building for Smart Cities: ASEAN Chief Smart City Officers (ASEAN-CSCOs)
Implementing Agency : | depa Thailand
Duration/Period : | 2025 (the commencement date depends on the approval) 12 Months
ADM2025 | E.A. 7.4 of ADM2025
Main Activity / Tasks | Task Description |  | Timeline Jan - Dec 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1. Management Arrangements |  |  | Feb | Mar | Apr | May | June | July | Aus | Sep | Oct | Nov | Dec
1.1 A project team will be formed, consisting of project managers, technical experts, and administrative staff. The project manager will be responsible for overall project coordination and management, ensuring that all activities are aligned with the project goals and timelines.
1.2 The project team will hold bi-weekly coordination meetings to track progress, address any issues, and make necessary adjustments. These meetings will include representatives from ADSOM and other related sectoral bodies such as ASCN and the MPAC Sectoral Body to ensure that regional perspectives and priorities are integrated into the project implementation.
1.3 A quarterly review meetings will be conducted with key stakeholders, including representatives from ASEAN member states, to provide updates on project progress and gather feedback.
2. Online Preparatory Engagements |  |  | Feb | Mar | Apr | May | June | July | Aus | Sep | Oct | Nov | Dec
2.1 A series of virtual sessions with stakeholders from ASEAN member states will be initiated to customize the workshop content, ensuring it addresses the unique urban development challenges of each participating city. | bar: Feb to Mar
2.2 The project team conducts needs assessments and pre-workshop surveys to identify priority areas for capacity-building and set clear learning objectives that align with the current smart city landscape of ASEAN. | bar: Feb to Mar
3. Experimental Workshop in Nakorn Si Thammarat |  | Jan | Feb | Mar | Apr | May | June | July | Aus | Sep | Oct | Nov | Dec
3.1 An interactive, on-site workshops in Nakhon Si Thammarat will be held to offer a hands-on look at the city's award-winning smart city initiatives. | bar: Apr to June
3.2 A practical demonstrations and field visits to key smart city projects, including the citizen e-service platform and flood prevention systems, will be arranged to facilitate direct knowledge transfer from local experts to participants. | bar: Apr to June
4. Online Collaboration Platform and Handbook Production |  | Jan | Feb | Mar | Apr | May | June | July | Aus | Sep | Oct | Nov | Dec
4.1 A post-workshopdigital forum, where ASEAN city representatives can continue to engage, will be organized to exchange experiences, and discuss ongoing challenges and successes in smart city development. | bar: Oct to Dec
4.2 A comprehensive handbook for smart cities will be developed to provide best practices, case studies, and strategic frameworks, providing a step-by-step guide to navigating the complexities of smart city development. | bar: Oct to Dec
4.3 A monthly progress reports will be prepared by the project team, detailing activities completed, challenges encountered, and plans for the upcoming month. | bar: Oct to Dec