Concept Note
ASEAN Digital Capacity Building for Smart Cities:
ASEAN Chief Smart City Officers (ASEAN-CSCOs) Programme 
Thailand 2025

INTRODUCTION & BACKGROUND

ASEAN member states are experiencing rapid urbanization and increasing pressure to deliver sustainable, inclusive, and citizen-centric urban services. While various smart city initiatives have emerged across the region, there remains uneven capacity among policymakers and implementers to design, execute, and scale solutions that respond to local needs and align with shared regional goals.

Thailand has demonstrated leadership in smart city development through national initiatives and capacity-building programmes, including training over 1,000 smart city professionals even during the pandemic. Building on this experience, Thailand will host the ASEAN Digital Capacity Building for Smart Cities: ASEAN Chief Smart City Officers (ASEAN-CSCOs) Programme in 2025.

The initiative is funded by the ASEAN ICT Fund and co-organized by the Digital Economy Promotion Agency (depa), reflecting a shared commitment to regional collaboration and inclusive digital development.

This programme builds on progress made under the ASEAN ICT Masterplan 2020 (AIM 2020) to strengthen the capacity of ASEAN member states to design and implement citizen-centric smart city strategies. It will bring together policymakers, planners, and technologists from ASEAN countries to engage in practical, hands-on learning, foster regional collaboration, and develop a shared vision for inclusive, digitally enabled urban development.

OBJECTIVES

The ASEAN-CSCOs Programme has the following key objectives:

- Build Practical Capacity: Equip ASEAN policymakers, urban planners, and technologists with practical skills to design and implement citizen-centric smart city initiatives.

- Foster Regional Collaboration: Strengthen regional cooperation and knowledge sharing among ASEAN member states to address shared urbanization challenges.

- Promote Inclusive and Sustainable Development: Support the development of digital governance frameworks that prioritize inclusivity, sustainability, and resilience.

- Integrate Public-Private Expertise: Engage private sector partners to share technological innovations and best practices that can enhance public sector planning and delivery.

THEME

Theme: “From Knowledge to Action: Advancing ASEAN Smart Cities through Citizen-Centric Smart City Approaches”

This theme emphasizes the importance of shifting focus from technology-driven development to citizen-centric approaches. Through the ASEAN Smart Cities Network (ASCN), member cities collaborate, exchange knowledge, and co-create practical actions that translate shared visions into measurable outcomes that genuinely improves citizens’ quality of life—turning regional cooperation and knowledge into collective action for a smarter, more people-centered ASEAN.

KEY COMPONENTS / ACTIVITIES

The ASEAN-CSCOs Programme will consist of three main components designed to deliver practical skills, foster collaboration, and create lasting resources for ASEAN member states:

- Online Preparatory Engagements will include virtual sessions to introduce key concepts, share regional case studies, and prepare participants for hands-on workshops while fostering initial networking among ASEAN participants.

- Experiential Workshops in Thailand will provide in-person, hands-on training in Nakhon Si Thammarat, featuring practical exercises on citizen-centric design, financing strategies, technology integration, and leadership in smart city development. The workshops will also engage private sector experts listed in the Thailand Digital Catalog to share innovations and global best practices.

- Online Collaborative Platform and Handbook Production will involve the development and distribution of the Handbook for Citizen-Centric Smart Cities, featuring best practices, frameworks, and case studies, as well as the launch of an online platform to enable continuous learning, peer-to-peer exchanges, and sustained collaboration across ASEAN.

DRAFT PROGRAMME

The ASEAN-CSCOs Programme will deliver a structured sequence of activities designed to support knowledge-building, regional collaboration, and the practical development of smart city strategies among ASEAN member states.

1. Online Preparatory Engagements (2 Webinars)

In the lead-up to the in-person sessions, participants will engage in two preparatory webinars aimed at building a shared foundation of understanding, encouraging peer exchange, and initiating contributions to the ASEAN Smart City Handbook.

Webinar 1: Orientation and Southern Smart City Insights

This session will welcome participants and provide an overview of the programme objectives and structure. It will feature case studies from southern Thailand to showcase real-world smart city applications, followed by a brainstorming activity to initiate the first group assignment for the development of the ASEAN Smart City Handbook.

Webinar 2: Citizen-Centric Strategies and Travel Preparation

The second webinar will begin with a recap and review of initial assignments. Participants will then engage in a knowledge-sharing session focused on citizen-centric smart city approaches. The Mayor of Nakhon Si Thammarat will offer welcoming remarks in anticipation of the on-site programme. The session will conclude with practical guidance on travel arrangements, logistics, and on-ground expectations.

These online sessions are designed to create early momentum, foster regional rapport, and ensure participants are well-prepared for the in-person workshops.

2. Experiential Workshops in Nakhon Si Thammarat, Thailand

Following the preparatory webinars, participants will convene in Nakhon Si Thammarat for a two-day immersive workshop designed to deepen practical understanding, strengthen collaboration, and co-develop knowledge products under real-world conditions.

Day 1: Local Perspectives and Field Immersion

Morning: City Presentations

Participants will receive briefings from the Nakhon Si Thammarat municipal team, showcasing the city’s digital transformation journey, urban challenges, and local innovations in smart city development.

Afternoon: Field Visit

A guided, three-hour site visit will allow participants to observe smart city projects in action. The visit aims to provide real-world context for policy discussions and inspire practical approaches for addressing urban challenges in diverse ASEAN contexts.

Evening: Summary and Networking Dinner

A facilitated session will summarize the day's key takeaways, followed by a networking dinner to encourage informal dialogue and relationship-building among participants, organizers, and local stakeholders.

Day 2: Practical Application and Collaborative Development

Morning: Collaborative Problem-Solving and Handbook Drafting

Participants will engage in a guided workshop to apply shared knowledge and tools to identify and propose solutions for specific urban “pain points.” This session will also initiate drafting of relevant sections of the ASEAN Smart City Handbook, ensuring local relevance and collective input.

Group Work and Peer Review

Participants will work in teams to refine their proposals and handbook contributions, with opportunities for peer feedback and expert guidance. The day will conclude with a synthesis of ideas and preparation for the next phase of the programme.

These experiential workshops aim to translate theory into practice, promote regional collaboration, and generate tangible outputs that contribute to the broader ASEAN smart city agenda.

3. Online Collaborative Platform and Handbook Production

To ensure sustained engagement and long-term impact beyond the in-person workshops, the ASEAN-CSCOs Programme will culminate in the development of key knowledge tools to support continued collaboration and practical application.

Handbook for Citizen-Centric Smart Cities

Participants will contribute to the creation of a regional handbook titled “Citizen-Centric Approach to Cope with City Pain Points.” This publication will compile case studies, policy insights, strategic frameworks, and practical tools drawn from programme activities. It is intended as a reference guide for policymakers, planners, and implementers across ASEAN, supporting the design and implementation of inclusive, context-sensitive smart city strategies.

Launch of the Online Collaborative Platform

A dedicated digital platform will be launched to enable ongoing peer-to-peer exchange, knowledge sharing, and collaboration among ASEAN smart city leaders. The platform will also serve as a repository for programme materials, resources, and future updates, helping to foster a sustained community of practice across the region.

4. Programme of activities

Note: Dates to be confirmed. All times are Thailand time (GMT+7)

| Date | Time | Activity | Venue / Notes |
| --- | --- | --- | --- |
| 10 November 2025 | 13.30 – 16.00 | Online Preparatory Engagement – Webinar #1- Greeting & Orientation- Smart City Southern Cases- Brainstorm & Assignment for Handbook | Virtual (Online platform link to be provided) |
| 13 November 2025 | 13.30 – 16.00 | Online Preparatory Engagement – Webinar #2- Recap & Assignment Review- Knowledge Sharing on Citizen-Centric Approach- Greeting by Nakhon Si Thammarat Mayor- Travel Plan and Logistics | Virtual (Online platform link to be provided) |
| 19 November 2025 |  | Arrival of Delegates |  |
| 20 November 2025 | 09.00 -12.00 | - Welcome and Context Setting- Presentations by Nakhon Si Thammarat Team (1.5 hrs) and Guest Expert (1.5 hrs) | Nakhon Si Thammarat, Thailand |
|  | 13.00 – 16.00 | - Field Visit in Nakhon Si Thammarat (3 hrs) | Activities designed by host |
|  | 18.00 – 20.00 | - Activity Summary - Networking Dinner | Venue details TBC |
| 21 November 2025 | 09.00 – 10.30 | - Group Work: Applying Knowledge to City Pain Points- Drafting Handbook Content | Nakhon Si Thammarat, Thailand |
|  | 10.30 – 12.00 | - Group Review and Wrap-Up Discussion | Nakhon Si Thammarat, Thailand |
|  |  | Participants will be traveling from the venue back to their home countries. |  |
| December 2025 (Date to be confirmed) |  | Online Collaborative Platform and Handbook Production- Handbook development and distribution- Online platform launch for peer exchange | Virtual (Details to be shared) Handbook theme: Citizen-Centric Approach to Cope with City Pain Points |
| December 2025 (Date to be confirmed) |  | Launch of the Online Collaborative Platform | Virtual (Online platform link to be provided) |

EXPECTED OUTCOMES

The ASEAN-CSCOs Programme will strengthen the capacity of ASEAN policymakers, urban planners, and technologists to design and implement citizen-centric, sustainable smart city strategies. Through structured learning, real-world application, and regional exchange, the programme will foster collaboration and knowledge sharing across member states, building long-term partnerships for inclusive urban development.

A key outcome will be the Handbook for Citizen-Centric Smart Cities, themed “Citizen-Centric Approach to Cope with City Pain Points.” This regional publication will consolidate best practices, policy frameworks, tools, and case studies, serving as a practical reference for current and future city leaders to scale effective solutions in diverse contexts.

The programme also aims to:

- Promote innovative technologies and data-driven approaches in smart city planning.

- Support pilot initiatives aligned with regional goals.

- Launch an online collaborative platform for continued engagement.

- Strengthen the regional foundation for smart city development under the ASEAN Smart Cities Network.

Together, these outcomes will advance ASEAN’s vision of inclusive, resilient, and digitally empowered cities.

IMPLEMENTATION ARRANGEMENTS

The Digital Economy Promotion Agency (depa), under the Ministry of Digital Economy and Society of Thailand, will serve as the main organizer and secretariat, overseeing planning, coordination, and delivery of all programme activities in close collaboration with ASEAN member states.

A dedicated project team will manage workshops, develop learning resources, coordinate logistics, and ensure effective communication with participants and stakeholders.

APPLICATION REQUIREMENTS

To participate in the project, applicants are required to meet the following conditions and provide the necessary documents:

PARTICIPANT ELIGIBILITY

Applicants must meet the following criteria:

- Professionals who are government officials, urban planners, or technologists from ASEAN Member States.

- A minimum of 10 years of experience is preferred in smart city planning, urban development, digital governance, or related policy areas.

- Officially nominated by their Ministry or Agency via an official nomination letter.

- Able to fully participate in all program components, including online webinars, in-person workshops, and the online collaborative platform.

- Proficient in English, as all program activities will be conducted in English.

APPLICATION PROCEDURE

- Complete the online application form https://short.depa.or.th/h3rai

- Download letter of nomination https://short.depa.or.th/QmIHI

- Ensure all required documents are uploaded by 30 October 2025

- Late or incomplete applications will not be considered.

COVERAGE

Thailand, as the host country, will provide:

- Airfare: Round-trip support (one representative per ASEAN Member State), capped at USD 700.

- Per diem: USD 200 per participant per day.

- Workshop support: Facilities, meals, and local transportation during the workshop.

- Complimentary shuttle transfer: Suvarnabhumi to Don Mueang for Nakhon Si Thammarat flights (time slots to be announced)